## Export
Non HHH-FUNDED HOUSING DEVELOPMENT
PROGRESS REPORT
10/2024
Project Number | Project Name | Developer | Address | NOFA Round | Program Activity | CD | State Sen Dist | Assembly Dist | Congressional Dist | TOD | Amt Finance | SH Units | NonSH UNITS | Mgr Units | Total Units | Admit date | Loan Closed (Estimated) | Loan Closed (Actual) | In-Construction (Estimated) | In-Construction (Actual) | Ready For Occupancy (Estimated) | Ready For Occupancy (Actual)
21-128634 | First Street North-A (Go For Broke Apt N-4p) | LTSC Community Development Corporation | 200 N JUDGE JOHN AISO ST CA 90012 | HCIDLA 2021 AHMP NOFA | AHBP and AHMP | 14 | 24 | 53 | 34 | TOD | 19000000 | 52 | 129 | 2 | 181 | 2021-11-29 |  | 01/19/2024 |  | 02/02/2024 | 03/31/2026
21-127856 | Parkview Affordable Housing | Thomas Safran &amp; Associates | 4020 S COMPTON AVE CA 90011 |  | AHSC Only | 9 | 33 | 59 | 40 | NonTOD |  | 31 | 95 | 1 | 127 | 2019-11-19 |  | 07/22/2022 | 06/30/2025 |  | 06/30/2027
22-128928 | Jordan Downs Area 3B (fka H2B) (Bridge) | BRIDGE Housing Corporation | 2254 E 97TH ST CA 90002 |  | AHSC Only | 15 | 35 | 64 | 44 | N/A |  | 30 | 89 | 1 | 119 | 2020-09-01 |  | 07/21/2023 | 10/31/2024 |  | 10/31/2026
21-128633 | Crocker (Umeya) Apartments | LTSC Community Development Corporation | 411 S TOWNE AVE CA 90013 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 14 | 30 | 53 | 34 | TOD | 10180000 | 87 | 86 | 2 | 175 | 2021-11-29 |  | 04/18/2023 |  | 04/27/2023 | 05/01/2026
22-128926 | Vista Terrace | Thomas Safran &amp; Associates Development Inc. | 8134 N VAN NUYS BLVD CA 91402 |  | Bond Only | 6 | 18 | 46 | 29 | TOD |  | 24 | 77 | 1 | 102 | 2020-09-01 |  | 03/06/2023 |  | 05/01/2023 | 04/02/2025
15-123418 | Westmore Elden Elms Ph2 | West Hollywood Community Housing Corporation | 1255 S ELDEN AVE Los Angeles, CA 90006 |  | 9% Tax Credit Only | 1 | 24 | 53 | 34 | TOD |  | 15 | 77 | 1 | 93 | 2015-11-03 |  | 03/06/2019 |  | 03/01/2019 |  | 02/03/2021
15-122540 | Westmore Linden Seniors (Phase 1) | West Hollywood Community Housing Corporation | 1250 S WESTMORELAND AVE Los Angeles, CA 90006 |  | 9% Tax Credit Only | 1 | 24 | 53 | 34 | TOD |  | 15 | 77 | 1 | 93 | 2015-11-03 |  | 03/15/2018 |  | 04/02/2018 |  | 01/24/2020
21-128638 | Menlo Ave Apartments | Omni America LLC; Cypress Menlo LLC; TWD Menlo, LLC | 1216 S MENLO AVE CA 90006 |  | AHBP and AHMP | 1 | 24 | 53 | 34 | TOD | 6300000 | 50 | 76 | 1 | 127 | 2021-11-29 | 02/14/2025 |  | 02/25/2025 |  | 02/08/2027
15-122400 | Sylmar Court Apts. | Meta Housing Corporation | 12415 N SAN FERNANDO RD SYLMAR, CA 91342 | May 2015 Call for Projects | AHBP and AHMP | 7 | 18 | 39 | 29 | TOD | 5975000 | 25 | 75 | 1 | 101 | 2015-11-03 |  | 01/21/2016 |  | 06/16/2016 |  | 12/30/2017
15-122539 | Arminta Square | Meta Housing Corporation | 11050 W ARMINTA ST Sun Valley, CA 91352 |  | 9% Tax Credit Only | 6 | 18 | 39 | 29 | NonTOD |  | 45 | 64 | 1 | 110 | 2015-11-03 |  | 09/26/2019 |  | 10/01/2019 |  | 02/26/2021
21-128643 | The Arlington | Thomas Safran &amp; Associates Development, Inc. | 3322 W WASHINGTON BLVD CA 90018 | HCIDLA 2021 AHMP NOFA | AHBP and AHMP | 10 | 30 | 54 | 37 | NonTOD | 6300000 | 20 | 63 | 1 | 84 | 2021-11-29 |  | 11/03/2023 |  | 02/05/2024 | 10/05/2025
14-121611 | Mosaic Gardens at Westlake, fka Beverly & Lucas | LINC Housing Corporation | 1416 W BEVERLY BLVD Los Angeles, CA 90026 | Jan 2014 Call for Projects-Submission of Documents | Affordable Hsg Managed Pipeline | 1 | 24 | 51 | 34 | TOD | 6690000 | 63 | 60 | 2 | 125 | 2014-06-16 |  | 03/16/2016 |  | 05/18/2016 |  | 06/29/2018
21-128636 | Red Tail Crossing (fka Kite Crossing) | Community Corporation of Santa Monica | 8333 S AIRPORT BLVD CA 90045 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 11 | 26 | 62 | 43 | NonTOD | 1200000 | 40 | 60 | 2 | 102 | 2021-11-29 |  | 12/15/2022 |  | 01/06/2023 | 11/20/2024
19-128219 | Vermont Manchester Family Transit Priority Project | BRIDGE Housing Corporation | 8500 S VERMONT AVE CA 90044 |  | AHSC Only | 8 | 30 | 59 | 43 | TOD |  | 58 | 58 | 2 | 118 | 2018-10-30 |  | 06/03/2022 | 10/31/2024 |  | 10/31/2026
14-121652 | Florence Mills | Hollywood Community Housing Corporation | 1036 E 35TH ST LOS ANGELES, CA 90011 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 9 | 30 | 59 | 40 | TOD | 9389115.63 | 19 | 54 | 1 | 74 | 2014-01-21 |  | 12/17/2018 |  | 12/27/2018 |  | 03/24/2021
17-124942 | Metro at Buckingham aka Buckingham Phase 2 | Meta Housing Corporation | 4018 S BUCKINGHAM ROAD Los Angeles, CA 90008 |  | 9% Tax Credit Only | 10 | 30 | 54 | 37 | TOD |  | 51 | 51 | 1 | 103 | 2017-11-16 |  | 12/13/2018 |  | 12/18/2018 |  | 11/23/2020
21-128644 | Third Thyme | West Hollywood Community Housing Corporation | 1435 W 3RD ST CA 90017 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 1 | 24 | 51 | 34 | TOD | 11873930 | 52 | 50 | 2 | 104 | 2021-11-29 |  | 05/04/2023 |  | 05/24/2023 | 08/21/2025
21-128635 | First Street North- B/South (fkaGo For Broke S 9p) | LTSC Community Development Corporation | 128 N JUDGE JOHN AISO ST CA 90012 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 14 | 24 | 53 | 34 | TOD | 6805200 | 17 | 49 | 1 | 67 | 2021-11-29 |  | 01/18/2024 |  | 02/02/2024 | 03/31/2026
21-128639 | Miramar Gold | West Hollywood Community Housing Corporation | 1434 W MIRAMAR ST LOS ANGELES, CA 90026 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 1 | 24 | 51 | 34 | TOD | 13806150 | 47 | 46 | 1 | 94 | 2021-11-29 |  | 10/11/2022 |  | 10/27/2022 | 05/19/2025
20-126937 | Palm Vista Apartments | HCHC Palm Vista MGP, L.L.C.; GTM Palm Vista AGP, L.L.C. | 20116 W SHERMAN WAY Winnetka, CA 91306 |  | Bond Only | 3 | 27 | 45 | 30 | TOD | 29700000 | 44 | 45 | 2 | 91 | 2020-09-22 |  | 07/07/2021 |  | 07/30/2021 |  | 08/29/2023
23-130492 | Crenshaw and 50th | Michaels Development Company | 5002 S CRENSHAW BLVD Los Angeles, CA 90043 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline | 8 | 30 | 54 | 37 | TOD | 4390000 | 15 | 44 | 1 | 60 | 2023-04-25 | 04/01/2025 |  | 04/07/2025 |  | 04/01/2027
23-130508 | Jordan Downs Phase S5 | Michaels Development Company | S Lou Dillon AVE Los Angeles, CA 90002 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline |  |  |  |  | TOD | 13349206 | 20 | 44 | 1 | 65 | 2023-04-25 | 12/01/2024 |  | 12/05/2024 |  | 06/30/2025
23-131875 | Alveare Family |  | 1405 S BROADWAY CA 90015 | 1 | Affordable Hsg Managed Pipeline | 14 | 30 | 53 | 34 | N/A | 10559557 | 62 | 42 | 1 | 105 |  | 05/09/2025 |  | 06/09/2025 |  | 06/09/2026
20-128217 | Corazon del Valle | Clifford Beers Housing, Inc. | 14545 W LANARK ST CA 91402 |  | AHSC Only | 6 | 18 | 46 | 29 | TOD |  | 49 | 39 | 2 | 90 | 2019-10-30 |  | 06/11/2021 |  | 06/23/2021 |  | 03/02/2022
21-128410 | 619 Westlake (fka Westlake 619) | Meta Housing Corporation | 619 S WESTLAKE AVE Los Angeles, CA 90057 |  | Bond Only | 1 | 22 | 46 | 34 | TOD | 3149580 | 39 | 38 | 1 | 78 | 2019-10-15 |  | 10/21/2021 |  | 11/04/2021 |  | 11/16/2023
20-126934 | La Prensa Libre - 4% | AMCAL Multi-Housing Inc | 210 E WASHINGTON BLVD Los Angeles, CA 90015 | HCIDLA May 2018 Call For Projects | Affordable Hsg Managed Pipeline | 9 | 30 | 59 | 37 | TOD | 6334820 | 25 | 37 | 1 | 63 | 2018-10-20 |  | 11/18/2020 |  | 11/30/2020 |  | 01/30/2024
23-130493 | Grace Villas | Women Organizing Resources, Knowledge and Services | 216 S AVENUE 24 Los Angeles, CA 90031 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline | 1 | 24 | 51 | 34 | TOD | 11995973 | 12 | 35 | 1 | 48 | 2023-04-25 | 04/02/2025 |  | 04/02/2025 |  | 04/02/2026
21-128637 | Luna Vista Apartments | Hollywood Community Housing Corporation | 8767 N PARTHENIA PL 1-73 LOS ANGELES, CA 91343 | HCIDLA 2021 AHMP NOFA | AHBP and AHMP | 6 | 18 | 46 | 29 | NonTOD | 3767626 | 36 | 35 | 2 | 73 | 2021-11-29 |  | 11/18/2022 |  | 12/09/2022 | 12/31/2024
15-122532 | Pico Robertson Senior Community | Mercy Housing California | 8866 W PICO BLVD LOS ANGELES, CA 90035 | May 2015 Call for Projects | Affordable Hsg Managed Pipeline | 5 | 30 | 50 | 37 | TOD | 2789400 | 12 | 35 | 0 | 47 | 2015-11-03 |  | 12/01/2017 |  | 02/19/2018 |  | 08/07/2020
21-128642 | Venice Dell (fka Reese Davidson Comm) | Hollywood Community Housing Corporation; Hollywood Community Housing Corporation; Venice Community Housing Corporation | 2102 S PACIFIC AVE CA 90291 | HCIDLA 2021 AHMP NOFA | AHBP and AHMP | 11 | 26 | 62 | 33 | TOD | 9649000 | 31 | 30 | 2 | 63 | 2021-11-29 | 11/30/2024 |  | 12/30/2024 |  | 11/30/2026
23-130498 | The Carlton | Abode Communities | 5401 S WESTERN AVE Los Angeles, CA 90062 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline | 8 | 30 | 54 | 37 | TOD | 7771750 | 30 | 29 | 1 | 60 | 2023-04-25 |  | 04/09/2024 |  | 05/31/2024 | 06/10/2026
23-130505 | Central Avenue Apartments | Abode Communities | 8909 S CENTRAL AVE Los Angeles, CA 90002 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline | 9 | 30 | 59 | 43 | TOD | 6221279 | 30 | 28 | 1 | 59 | 2023-04-25 |  | 04/09/2024 |  | 06/04/2024 | 06/22/2026
14-121639 | Ybarra Village (fka New Directions West Adams) | D.L. Horn &amp; Associates LLC | 3023 1/2 S WEST VIEW ST LOS ANGELES, CA 90016 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 10 | 30 | 54 | 37 | TOD | 7167718 | 36 | 27 | 1 | 64 | 2014-01-21 |  | 11/27/2017 |  | 01/03/2018 |  | 12/20/2019
15-122534 | 7th & Witmer Apartments | Deep Green Housing and Community Development | 1301 W 7TH ST LOS ANGELES, CA 90017 | May 2015 Call for Projects | Affordable Hsg Managed Pipeline | 1 | 24 | 53 | 34 | TOD | 1500000 | 50 | 25 | 1 | 76 | 2015-11-03 |  | 12/14/2017 |  | 04/04/2018 |  | 12/31/2019
21-128632 | Alvarado Kent Apartments | SRO Housing Corporation (Dev) | 707 N ALVARADO ST LOS ANGELES, CA 90026 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 13 | 24 | 51 | 28 | TOD | 10441645 | 60 | 20 | 1 | 81 | 2021-11-29 |  | 12/20/2022 |  | 01/31/2023 | 12/30/2024
15-122549 | Metro at Western | Meta Housing Corporation | 3651 S WESTERN AVE Los Angeles, CA 90018 |  | 9% Tax Credit Only | 8 | 30 | 54 | 37 | TOD |  | 16 | 16 | 1 | 33 | 2015-11-03 |  | 12/01/2017 |  | 12/03/2017 |  | 03/12/2019
15-122536 | Cielito II- 1st and Soto TOD Apts Phase II | East LA Community Corporation | 2423 3/4 E 1ST ST LOS ANGELES, CA 90033 | May 2015 Call for Projects | Affordable Hsg Managed Pipeline | 14 | 24 | 53 | 34 | TOD | 2050000 | 14 | 14 | 1 | 29 | 2015-11-03 |  | 03/29/2018 |  | 05/25/2018 |  | 12/31/2019
14-121650 | PATH Metro Villas Phase I | PATH Ventures; Affirmed Housing Group, Inc. | 345 N WESTMORELAND AVE LOS ANGELES, CA 90004 | July 2013 Initial Call For Projects (Phase II) | AHBP and AHMP | 13 | 24 | 53 | 34 | TOD | 8472548 | 51 | 13 | 1 | 65 | 2014-01-21 |  | 07/26/2016 |  | 12/22/2016 |  | 08/31/2018
22-128927 | Locke Lofts | Flexible PSH Solutions, Inc. | 345 N MADISON AVE CA 90004 |  | AHBP and AHMP | 13 | 24 | 53 | 34 | N/A | 12995146 | 137 | 9 | 2 | 148 | 2020-09-01 | 12/11/2024 |  | 12/11/2024 |  | 12/11/2026
14-121118 | Marmion Way Apartments | D.L.Horn &amp; Associates, LLC | 3500 N MARMION WAY Los Angeles, CA 90065 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 1 | 24 | 51 | 34 | TOD | 5315691 | 40 | 8 | 1 | 49 | 2014-01-21 |  | 03/18/2015 |  | 04/30/2015 |  | 12/29/2016
15-122555 | Sun Valley Senior Veterans Apartments | East LA Community Corporation | 9041 N LAUREL CANYON BLVD SUN VALLEY, CA 91352 |  | Bond Only | 6 | 18 | 39 | 29 | TOD |  | 93 | 1 | 1 | 96 | 2015-11-03 |  | 01/23/2018 |  | 02/26/2018 |  | 05/04/2020
14-121649 | 127th Street Apartments | Meta Housing Corporation | 550 W 127TH ST Los Angeles, CA 90044 | Jan 2014 Call for Projects-Submission of Documents | AHBP and AHMP | 15 | 35 | 64 | 43 | TOD | 4450000 | 84 | 0 | 1 | 85 | 2014-06-16 |  | 01/21/2016 |  | 09/06/2016 |  | 07/26/2018
20-131133 | 15230 Parthenia HACLA Phk1 | Housing Authority of the City of Los Angeles (HACLA) | 15230 W PARTHENIA ST CA 91343 |  | SH Count for Dashboard | 6 | 18 | 46 | 29 | N/A |  | 40 | 0 | 1 | 41 |  |  | 12/02/2020 |  | 12/02/2020 |  | 12/02/2020
20-131132 | 1643 N Martel Ave HACLA phk1 | Housing Authority of the City of Los Angeles (HACLA) | 1643 N MARTEL AVE HOLLYWOOD, CA 90046 |  | SH Count for Dashboard | 4 | 26 | 50 | 28 | N/A |  | 11 | 0 | 0 | 11 |  |  | 12/30/2020 |  | 12/30/2020 |  | 12/30/2020
23-131711 | 3705 McLaughlin- PHK3 HACLA | Housing Authority of the City of Los Angeles (HACLA) | 3705 S MCLAUGHLIN AVE CA 90066 |  | HomeKey | 11 | 30 | 54 | 37 | TOD | 11530462 | 24 | 0 | 1 | 25 |  | 11/29/2024 |  | 12/02/2024 |  | 02/03/2025
23-131797 | 4818 N Sepulveda PHK3- HACLA | Housing Authority of the City of Los Angeles (HACLA) | 4818 N SEPULVEDA BLVD SHERMAN OAKS, CA 91403 |  | HomeKey | 4 | 18 | 46 | 30 | NonTOD |  | 34 | 0 | 1 | 35 |  | 12/03/2024 |  | 12/04/2024 |  | 03/03/2025
22-128362 | 600 San Pedro 1 | Weingart Center Association | 600 S SAN PEDRO ST CA 90014 |  | SH Count for Dashboard | 14 | 30 | 53 | 34 | NonTOD |  | 147 | 0 | 3 | 150 |  |  | 07/28/2023 |  | 07/31/2023 | 06/30/2025
22-128363 | 600 San Pedro 2 | Weingart Center Association | 600 S SAN PEDRO ST CA 90014 |  | SH Count for Dashboard | 14 | 30 | 53 | 34 | N/A |  | 151 | 0 | 1 | 152 |  |  | 07/28/2023 |  | 07/31/2023 | 06/30/2025
14-121637 | Arlington Square | A Community of Friends | 3101 W VENICE BLVD Los Angeles, CA 90019 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 10 | 30 | 54 | 37 | TOD | 3877600 | 47 | 0 | 1 | 48 | 2014-01-21 |  | 12/01/2015 |  | 12/04/2015 |  | 06/29/2017
22-131097 | Avenida PHK2 County | County of Los Angeles; Holos Communities (aka Clifford Beers Housing) | 321 N VERMONT AVE CA 90004 |  | SH Count for Dashboard | 13 | 24 | 53 | 34 | N/A |  | 75 | 0 | 1 | 76 |  |  | 06/22/2022 |  | 09/06/2022 |  | 08/04/2023
21-131819 | Best Inn (Mollie Mason) PHK1 | The People Concern | 4701 W ADAMS BLVD Los Angeles, CA 90016 |  | HomeKey | 10 | 30 | 54 | 37 | N/A |  | 22 | 0 | 1 | 23 | 2021-11-23 | 01/17/2025 |  | 02/03/2025 |  | 05/05/2025
20-131130 | Best Western NoHo- HACLA PHK1 | Housing Authority of the City of Los Angeles (HACLA); Housing Authority of the City of Los Angeles (HACLA) | 11135 W BURBANK BLVD NORTH HOLLYWOOD, CA 91601 |  | SH Count for Dashboard | 2 | 18 | 39 | 29 | N/A |  | 69 | 0 | 1 | 70 |  |  | 12/22/2021 |  | 12/22/2021 |  | 12/22/2021
14-121629 | Beverly Terrace | A Community of Friends | 3322 W BEVERLY BLVD LOS ANGELES, CA 90004 | Jan 2014 Call for Projects-Submission of Documents | AHBP and AHMP | 13 | 24 | 53 | 34 | TOD | 7332409 | 39 | 0 | 1 | 40 | 2014-06-16 |  | 12/18/2015 |  | 12/21/2015 |  | 01/04/2018
15-122548 | Casa Carmen Senior Apartments | 1010 DEVELOPMENT CORPORATION | 1800 W 11TH ST Los Angeles, CA 90006 | May 2015 Call for Projects | AHBP and AHMP | 1 | 24 | 53 | 34 | NonTOD | 2580000 | 24 | 0 | 1 | 25 | 2015-11-03 |  | 06/21/2017 |  | 07/17/2017 |  | 03/27/2019
15-122546 | El Segundo Apartments | Meta Housing Corporation | 535 W EL SEGUNDO BLVD Los Angeles, CA 90248 | May 2015 Call for Projects | AHBP and AHMP | 15 | 35 | 64 | 43 | TOD | 4000000 | 74 | 0 | 1 | 75 | 2015-11-03 |  | 07/25/2016 |  | 11/30/2016 |  | 07/26/2018
22-128372 | Jovenes (4th St) | Restore Neighborhoods Los Angeles (RNLA) | 3551 E 4TH ST CA 90063 |  | SH Count for Dashboard | 14 | 24 | 53 | 34 | NonTOD |  | 8 | 0 | 0 | 8 |  |  | 05/15/2022 |  | 07/20/2022 | 11/01/2024
14-121612 | King 1101 | Clifford Beers Housing, Inc. | 1107 W MARTIN LUTHER KING BLVD Los Angeles, CA 90037 | Jan 2014 Call for Projects-Submission of Documents | Affordable Hsg Managed Pipeline | 8 | 30 | 59 | 37 | TOD | 4130000 | 25 | 0 | 1 | 26 | 2014-06-16 |  | 07/20/2016 |  | 01/17/2017 |  | 09/07/2018
18-124761 | LAMP Lodge | Meta Housing Corporation | 660 S STANFORD AVE Los Angeles, CA 90021 | September 2016 Call for Projects | Affordable Hsg Managed Pipeline | 14 | 30 | 53 | 34 | TOD | 4070740 | 81 | 0 | 1 | 82 | 2017-11-16 |  | 12/16/2019 |  | 04/24/2020 |  | 10/04/2022
21-128361 | Marian Place | Venice Community Housing Corp. | 2213 S MARIAN PL CA 90291 |  | SH Count for Dashboard | 11 | 26 | 62 | 33 | N/A |  | 8 | 0 | 1 | 9 |  |  | 11/17/2021 |  | 11/21/2021 |  | 07/30/2024
14-121647 | Panama Hotel Apartments | Single Room Occupancy Housing Corporation | 403 E 5TH ST Los Angeles, CA 90013 | Jan 2014 Call for Projects-Submission of Documents | Affordable Hsg Managed Pipeline | 14 | 30 | 53 | 34 | TOD | 4489380 | 71 | 0 | 1 | 72 | 2014-06-16 |  | 03/16/2016 |  | 04/01/2016 |  | 10/20/2017
18-125455 | PATH Villas Montclair/Gramercy(Recap-Site 2 of 2) | PATH Ventures | 3317 W WASHINGTON BLVD Los Angeles, CA 90018 | HCIDLA May 2018 Call For Projects | AHBP and AHMP | 10 | 30 | 54 | 37 | TOD | 3029558 | 16 | 0 | 1 | 17 | 2017-10-19 |  | 12/26/2019 |  | 12/23/2020 |  | 07/26/2022
21-128640 | Prisma (fka Orange and DeLongpre Apartments) | Affirmed Housing Group, Inc. | 6914 W DE LONGPRE AVE HOLLYWOOD, CA 90028 | HCIDLA 2021 AHMP NOFA | Affordable Hsg Managed Pipeline | 13 | 26 | 50 | 28 | NonTOD | 7341441 | 96 | 0 | 2 | 98 | 2021-11-29 | 02/03/2025 |  | 02/03/2025 |  | 02/03/2027
14-121713 | Rampart Mint Apartments | West Hollywood Community Housing Corp. | 252 S RAMPART BLVD LOS ANGELES, CA 90057 | July 2013 Initial Call For Projects (Phase II) | AHBP and AHMP | 13 | 24 | 51 | 34 | TOD | 5150060 | 22 | 0 | 1 | 23 | 2014-01-21 |  | 12/13/2017 |  | 03/05/2018 |  | 11/09/2020
23-130504 | Rosa's Place (fka Downtown Womens Ctr Campus Exp) | GTM Holdings, LLC; Daylight Community Develoment, LLC; Downtown Women's Center | 501 E 5TH ST Los Angeles, CA 90013 | 2022 LAHD AHMP NOFA | Affordable Hsg Managed Pipeline | 14 | 30 | 53 | 34 | TOD | 7785104 | 97 | 0 | 1 | 98 | 2023-04-25 | 02/03/2025 |  | 02/03/2025 |  | 02/03/2027
22-131800 | Roscoe HACLA PHK2 | Housing Authority of the City of Los Angeles (HACLA) | 14949 W ROSCOE BLVD CA 91402 |  | SH Count for Dashboard | 6 | 18 | 46 | 29 | N/A |  | 28 | 0 | 1 | 29 |  |  | 10/05/2021 |  | 11/01/2022 |  | 01/15/2023
22-131096 | Sea Rock Inn (Willows) PHK2 County | County of Los Angeles | 14032 S VERMONT AVE 1-52 CA 90247 |  | SH Count for Dashboard | 15 | 35 | 64 | 43 | N/A |  | 52 | 0 | 1 | 53 |  |  | 06/15/2022 |  | 04/24/2023 |  | 06/04/2024
20-132193 | Sieroty phk1 (aka Howard Johnson) |  | 7432 N RESEDA BLVD 1-74 CA 91335 |  | HomeKey | 4 | 27 | 45 | 30 | N/A |  | 73 | 0 | 1 | 74 |  | 12/20/2024 |  | 01/14/2025 |  | 10/07/2025
14-121640 | Silver Star Apartments/fka West Villas | A Community of Friends | 6570 S WEST BLVD Los Angeles, CA 90043 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 8 | 30 | 62 | 37 | TOD | 2519384 | 48 | 0 | 1 | 49 | 2014-01-21 |  | 12/01/2015 |  | 12/04/2015 |  | 06/07/2017
20-131129 | Super 8 Canoga Park- HACLA PHK1 | Housing Authority of the City of Los Angeles (HACLA) | 7631 N TOPANGA CANYON BLVD CA 91304 |  | SH Count for Dashboard | 3 | 27 | 45 | 30 | N/A |  | 51 | 0 | 1 | 52 |  |  | 11/13/2020 |  | 11/14/2020 |  | 06/03/2024
14-121712 | T. Bailey Manor | Women Organizing Resources, Knowledge and Services | 4121 N EAGLE ROCK BLVD LOS ANGELES, CA 90065 | July 2013 Initial Call For Projects (Phase II) | AHBP and AHMP | 1 | 24 | 51 | 34 | NonTOD | 4740000 | 45 | 0 | 1 | 46 | 2014-02-21 |  | 07/20/2015 |  | 01/04/2016 |  | 08/09/2017
14-121651 | The Fiesta (fka The Campus at L.A. Family Housing) | L.A. Family Housing Corporation | 7860 N Simpson AVE Los Angeles, CA 91605 | July 2013 Initial Call For Projects (Phase II) | Affordable Hsg Managed Pipeline | 6 | 18 | 39 | 29 | NonTOD | 2900000 | 49 | 0 | 1 | 50 | 2014-01-21 |  | 04/13/2016 |  | 06/07/2016 |  | 12/28/2017
20-131128 | The Orchid- HACLA PHK1 | Housing Authority of the City of Los Angeles (HACLA) | 1753 N ORCHID AVE 1-36 HOLLYWOOD, CA 90028 |  | SH Count for Dashboard | 13 | 26 | 50 | 28 | N/A |  | 39 | 0 | 1 | 40 |  |  | 03/11/2021 |  | 03/11/2021 |  | 03/11/2021
23-130736 | The Pano- PHK1 | LA Family Housing Corporation | 8209 N SEPULVEDA BLVD LOS ANGELES, CA 91402 |  | HomeKey | 6 | 18 | 46 | 29 | TOD | 9950000 | 90 | 0 | 1 | 91 |  |  | 04/22/2024 |  | 04/23/2024 | 09/26/2025
18-125018 | West Third Apartments | Veterans Housing Partnership, LLC | 1900 W 3RD ST Los Angeles, CA 90057 |  | AHBP and AHMP | 1 | 24 | 53 | 34 | TOD | 14386213 | 136 | 0 | 1 | 137 | 2018-02-23 |  | 12/27/2018 |  | 03/02/2020 |  | 05/04/2023
Applied filters: ProgramActivity is 9% Tax Credit Only, Affordable Hsg Managed Pipeline, AHBP and AHMP, AHSC Only, Bond Only, SH Count for Dashboard, or HomeKey